## Planning
Ref | Item | Description | Applicable (Y/N) | Complete (Y/N) | Notes (e.g. owner, location, link to items)
Event Space Logistics
Understanding and planning for the space used in delivering the Call for Code Day
L1 | Plan Call for Code Dates | Identify best dates for your organization to execute the Call for Code day. Allocate lead time for recruiting your developers and other participants and at least 3 weeks after the day for projects to be finalized before the August 31st deadline
L2 | Determine Hours | Based on your participant audience and/or location constraints, determine if continuous (e.g. overnight) coding will be part of the execution plan. Identify total planned coding time before collecting submissions for judging, allocate 24 - 36 hours for coding.
L3 | Size estimates | Plan out how "big" the event will be. Events of this type at a single location work well with up to several hundred participants or more. Participants will form teams of up to 5 members so the total number of projects to expect to judge will be much smaller
L4 | Event Location | Given the dates, hours of operation and size, schedule a venue that can provide both open space for presentations (kickoff, workshops, project judging) as well as tables for teams with power, good wifi, and a place for snacks. It may be the same space, or multiple spaces, like an auditorium and a cafeteria.
L5 | Special Location Needs | Identify any special needs for the location to meet the personel and technical requirements. Think about having power outlets for all participants, screen/projector, additional requirements for cooling off hours or security / building access off hours.
L6 | Location preparation times | If a location will need special set up, be sure to schedule with enough buffer for set up and tear down of any special items. Plan a half-day for basic setup of power strips, tables and banners and additional time for more complex needs.
L7 | Location Budget | Identify and plan for any costs for additional items and standard space costs
Content and communications plan
Communicating with internal teams through the planning, execution and wrap-up for the Call for Code Day
C1 | Contact CSR Team | If appropriate, connect with your organization's corporate social responsibility team to review the Call for Code day. Recognition for employees for their time spent contributing to the cause through Call for Code should be recognized appropriately to the overall corporate social responsibility benchmarks. Identify any highlight opportunities, for example on an internal news or blog for both the initial promotion as well as follow-up recognition for top teams and all challenge submitters.
C2 | Recruiting kickoff | Broadcast an internal introduction to the Call for Code using the sample nurture email, customized with your organization's unique tracking sign up information. If appropriate, put out a call for some leaders to join you in planning the event, both for logistics as well as technical organization and use case selection. You should also register for the challenge and visit to the developer.ibm.com/callforcode web site to learn more about challenge use cases and starter code patterns.
C3 | Identify target use cases | The overall context of disaster preparedness is very broad and the example use cases cover many dimensions. Find some time with design and strategy leads in your organization to help narrow down areas of focus within the use cases. Consider which timeframe around preparing for and mitigating natural disaster impact makes the most sense for your organization. It is in long-term planning, short-term warning, real-time help, or rebuilding and recovery. You can also select two or more of the six focus areas based on your organization's expertise and interests.
C4 | Create internal signup | Use an existing or create a simple internal registration process for confirming particpation and getting counts to assist in space and food logistics. Include in the internal registration a place for participants to identify any special dietary needs. Announce internally and include again the unique tracking sign up and call to action as a reminder for those that have not already registered.
C5 | Get your Box | Send an email to derek.teay@ibm.com with the number of developers that will be attending your Call for Code day and your shipping address
C6 | Order internal swag | IBM will be sending you a box of Call for Code swag for distribution during the Call for Code day, but as internal registrations are coming in, consider what other organization items you will want to also provide participants at or shortly after the event. Items can be door prizes or also recognition items to distribute as teams submit their projects to the challenge.
C7 | Promote - Banner(s) | Find one or more locations to put up some banners to promote and drive curiosity around the call for code. Print and hang simple posters in mail rooms, kitchens, and other social areas.
C8 | Preparation | With one week to go - preparation kicks into high gear. Send information out to participants with introductory steps including signing up for IBM Cloud accounts and attending virtual learning sessions and/or complete IBM Coder program challenges to gain experience and understanding of IBM Cloud. Finalize location logistics and verify swag and other items have arrived and are organized for participants.
C9 | Event execution Social | Use the Call for Code day as a point in time event for your corporate social responsibility program and general internal recognition programs. Invite members from those teams to join in for parts or all of the event to take pictures, make video interviews, or even join in with teams to provide their insights. Use the hashtag #CallforCode to promote your organization's day on social media.
C10 | Teams Follow-up | After the event, encourage the teams to keep going, take input from the judges and peers and take their MVP to a functional prototype or more. Use the sample nurturing email along with any statistics from the event or the challenge site about 1.5 weeks after the Call for Code day to remind teams that now is the time to power through and submit their projects.
C11 | Final reminder | Keep in touch with your teams, either informally or more formally while they work on their projects. Use the final sample nuture email to remind them to submit their projects and thank all participants in the orgnization. Check with your corporate social responsibility team if they want to also participate in recognition at this point.
Event Execution Logistics
Event execution details, food, flow, subject matter experts, judging
M1 | Meal planning | Work with the event location or your organization's preferred vendor to arrange for food, or do it yourself depending on size and complexity. Either way, you should be sure to consider special dietary needs that you can gather during planning. Allow for some creativity and feel free to expand on the ideas provided. Use rows below as needed to document the plan for keeping your participants happy and nourished.
M2 | Day 1 refreshments | Variety of drinks and snacks for a mid-morning start, plenty of water
M3 | Day 1 lunch | Box lunch, sandwiches, something that's easy to grab and go works well here since teams are forming and getting going with their ideation.
M4 | Day 1 afternoon snack | Grab and go snacks, plus drinks including coffee, tea and plenty of water
M5 | Day 1 dinner | Teams may be ready for a longer break but don't plan a 3 course sit down meal
M6 | Day 1 evening refreshments | If the venue will be open overnight, this may work well with light snacks early followed by late nite pizza
M7 | Day 2 breakfast | Have a few options beyond cereal, coffee, tea and water. Definitely time for some fresh fruit.
M8 | Day 2 snack / refreshments | Keep the fruit, add more drinks and snack bars.
M9 | Day 2 lunch | Box lunch, sandwiches, something that's easy to grab and go works well here since teams are now in the final push and have limited time
M10 | Day 2 afternoon snack | Variety of drinks and snacks and maybe something cheery and fun like popsicles or ice cream
M11 | Day 2 celebration dinner | Cap of the day with a bit of a party, or call it a day and let the teams go home and rest.
E1 | Unpack Box and Prepare | Stage any swag boxes, banners and other items into the space for the event. Set up tables and do final checks for network, a/v and any other items.
E2 | Event Kickoff | Welcome all participants, quickly cover ground rules and logistic items. Then have a senior leader in the organization kick off the event with a few words about why the team is responding to the Call for Code. Can use the provided introductory presentation or speak off-the-cuff for a few minutes (10-15).
E3 | Technical Introduction | Introduce the event and overall agenda for the Call for Code day. Use the provided Call for Code technical kickoff presentation to cover the chosen use cases and reference code patterns. As appropriate, include the material on IBM Cloud and Cloud services. Tip: Tune in to the IBM virtual kickoff overview presentations that are available for example talking points and how to demo IBM Cloud dashboard and access to services.
E4 | Team Formation | For smaller events, you can have a few individuals go up front right after the intro to pitch their team ideas and recruit members. Or, you can include team formation as part of the internal sign up or activities in the week before the event. However you choose to do this, make sure that each team has two developers to divide and conquer all that needs to be done over the next day
E5 | Subject Matter Experts | SME's can represent domain knowledge that apply to the use cases, or previous experience with IBM Cloud and other Call for Code sponsor/partner APIs. If there are enough SMEs available, one can be embedded in each team. Otherwise, set up a table, or have them work the floor and give advice and suggestions to teams.
E6 | Pitch Workshop | At or near the start of the second day, you can hold a brief pitch workshop using the provided presentation. Many common mistakes that get in the way of showing off a team's good work can be avoided. With just a short 15 minute time investment, teams will get a set of best practices to follow.
E6 | Judging | Plan to have Judging move quickly and keep teams on a consistent clock. For smaller events, having each team run their demo and pitch for the entire audience including judges is a great way to show off what they've done and get insights from peers, but at 3-5 minutes per presentation, having over 30 teams do this will take a lot of time. In that case, it's better for there to be teams of judges who go around to talk to each team in a science-fair format, then compare notes and select finalists. Then, the finalists (5-8) can all do pitches to the full audience in a shorter session.
E7 | Recognition | Unlike a competitive hackathon which often ends when the judges award prizes, the Call for Code day is for most teams the start of their journey to submitting a project to the challenge. As such, think of how to recognize each team that aligns to your organization's corporate social responsibility strategy. Of course, everybody gets a t-shirt!
E8 | Wrap up | Close the event by thanking the participants, subject matter experts and judges. Let the participants know that you will be following up to make sure they have what they need and are getting their projects submitted to the Call for Code challenge.

## Roles
Document the team you will have here, make extra copies of rows as needed for specific roles (e.g. Judge)
Role | Title | Description | Name | Job Title (if appropriate) | Business unit/Organization
PM | Captain | Project manager resonsible for organizing the Call for Code day overall, and referred to as the Captain responding to the call for their organization. | <your name here!>
CSR | Corporate Social Responsibility officer | Member of your organization leading strategy and execution of the corporate social resonsibility mission.
Marketing | Marketing Specialist | Organization Marketing contact who would assist in promoting internally and externally the Call for Code day, organize the press releases if needed, and coordinate the communications.
SME | Subject Matter Expert | Subject Matter Experts can represent domain knowledge that apply to the use cases, or previous experience with IBM Cloud and other Call for Code sponsor/partner APIs. They may also have development skills and participate in teams.
Judge | Judge | Member of the judging team. In addition to senior leaders and sponsors, include in the judging team members that can bring in a technical perspective for assessing the complexity and technical depth of the projects.
LoB | Line of Business / Analyst | Organization Line of Business representing the clients business views, needs and requirements. May be working in one team or across teams like an SME. | if members of the participant team, optional to list here given the #'s involved
UX | User Experience Specialist | User Experience specialist who can help developers design wireframes, storyboard and user interaction. Likely to have good coding, graphics, HTML and Javascript skills. | if members of the participant team, optional to list here given the #'s involved
Dev | Developer | Full stack developer with skills in modern agile coding techniques such as Node, Ruby, Python, Java, DOJO. | if members of the participant team, optional to list here given the #'s involved
Integrator | System Integragor | System developer / integrator who understands how to access back end systems and present data and services through RESTful APIs. | if members of the participant team, optional to list here given the #'s involved